MPUMALANGA PROVINCIAL GOVERNMENT

DELIVERY AGREEMENT FOR OUTCOME 12 AN EFFICIENT, EFFECTIVE AND DEVELOPMENT ORIENTED PUBLIC SERVICE AND AN EMPOWERED, FAIR AND INCLUSIVE CITIZENSHIP DATE: 08 DECEMBER 2010

LEAD DEPARTMENT: OFFICE OF THE PREMIER

TABLE OF CONTENTS

1.  OUTCOME PROBLEM STATEMENT	3

2.  OUTPUT 1 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS	4

3.  OUTPUT 2 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS	10

4.  OUTPUT 3 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS	14

5.  OUTPUT 4 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS	18

6.  OUTPUT 5 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS	22

7.  KEY DELIVERY PARTNERS	25

8.  SIGNATORIES	26

# 1.  OUTCOME PROBLEM STATEMENT

- While progress has been made in many areas of government work, the overall capacity of the state to accelerate the progressive realization of socio-economic rights remains a challenge.

- There are still gaps and challenges in a number of areas with regard to the state’s performance in achieving an effective, efficient and development orientated public service and an empowered, fair and inclusive citizenship.  These areas include amongst others:

  - The quality and accessibility of public services;

  - Inefficiencies in critical areas of service delivery

  - Ineffective implementation of performance management systems,  supply management systems, including procurement

- In part, enhancing the performance of government depends on our ability to attract and retain requisite skills, develop the skills base, and implement effective systems of performance monitoring assessment, both at individual and organizational levels

- Institutional coherence and alignment to advance common goals as different spheres of government needs to be improved

  - Integrated planning

  - Integrated service delivery

  - Pooling of resources towards common outcomes

  - Implementation of efficient and effective monitoring and evaluation systems and tools

- The basis for a shared development agenda across the spheres of government begins with a shared data and information base for provincial planning and performance monitoring on a range of agreed indicators. Currently, department and municipalities use various sources of data for planning about the same local environment. The quality and integrity of baseline data  on development and service delivery indicators

- Effective public participation in governance processes remains a critical measure of inclusive citizenship.   Despite enabling legislative processes and guidelines, the quality of public participation and communication of government work remain relatively weak, resulting in perceived ‘social distance’ between communities and elected public representatives and government in general

# 2.  OUTPUT 1 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS

Output 1: Service Delivery Quality and Access

Output 1: Problem Statement

- Despite remarkable progress that the Province has made over the years in advancing the progressive realization of socio-economic rights, there continue to be areas of the Province plagued by underdevelopment, poverty and service delivery backlogs. These challenges are more pronounced in former Bantustans.

- Notwithstanding varied dimensions to recently experienced service delivery protests in our Province, there is acknowledgement that government has to increase the pace at which it is rolling out basic services such as water, sanitation and housing.

- Government services are still not equitably accessible to all citizens, especially those in rural areas. The challenges of geographic access and fragmented delivery of government services need special attention. Government services need to be delivered in an integrated manner to reduce costs and citizen inconvenience

- Artificial barriers of access to socio-economic development opportunities hinder the empowerment and social progress of target groups, including women, youth, children and persons with disabilities. Such entrenched systemic exclusion needs to be addressed.

- There is limited coordination, monitoring and evaluation of service delivery initiatives and projects, resulting in poor accountability by those tasked with service delivery responsibilities.

Output 1: Problem Statement (continues)

- An inseparable dimension of access is quality. Quality should always be commensurate with the value for money spent for the provision of a service. In some areas of government work, the unit costs for services are not competitive. There are instances where service providers are overcharging government for services. In part, inefficient bidding processes and poor contract management contribute to price inflation, thereby undermining the value for money principle.

High Level Interventions

- Adopt an Integrated Provincial Five Year Plan as a common reference to drive a shared development and service delivery agenda;

- Institutionalization of the outcomes based approach to planning, implementation and performance monitoring and evaluation;

- Develop Provincial Vision 2025 – A long-term Growth and Development Strategy for Mpumalanga;

- Establish a Centre for Provincial Statistical Information and Analysis (CPSIA);

- Develop an integrated access strategy for the Province;

- Develop e-governance framework to enable efficient and quality service delivery across key areas of government work.

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Service delivery quality and access | Improved integrated service delivery plans | Disintegrated Service Delivery Plans and Policies | Strengthen integrated planning and implementation. IDPs aligned to 5 Year Plan. Provincial Vision 2025 in place. | Provincial 5 year plan approved by EXCO. Coordinate and support the development of Delivery Agreements. | 2 900 | 880 |
|  | Approved Provincial M&E policy framework | Inadequate monitoring and evaluation systems and tools. | 100% implementation of Provincial M&E policy framework Fully functional information technology system | Provincial Monitoring and evaluation policy framework approved by EXCO. Set up requisite M&E capacity in departments. Initiate the process of acquiring an IT system for performance monitoring and evaluation | 2 972 | 889 |

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Service delivery quality and access | Credible and quality planning and performance monitoring information in the Province | Institutional coordination on statistical data inadequate | Centre for Provincial Statistical Information and Analysis (CPSIA) established | Memorandum of Understanding with Stats SA concluded CPSIA approved by Exco |  |  |
|  |  | No shared understanding on baseline data for some of the key development and service delivery indicators | Credible baseline data and provincial planning and performance information available | Set up requisite infrastructure and institutional coordination mechanisms |  |  |
|  | Government programmes fully integrating target groups | Only Gender equality mainstreaming framework in place | Gender, Disability and Children mainstreaming frameworks implemented | Development of Disability and children mainstreaming framework Implementation of Gender equality mainstreaming framework | 2 365 | 1 206 |
|  |  | 20% mainstreaming performance by departments | 80% mainstreaming compliance | 30% performance level |  |  |

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Service delivery quality and access | Customer satisfaction % improvement of service user satisfaction | To be determined | Improve level of user satisfaction | Develop standard tools to measure user satisfaction; Establish user satisfaction baseline |  |  |
|  | Responsiveness % improvement in service turnaround/ waiting times at service points | To be determined | Improved level of responsiveness | Establish a standard tools to measure responsiveness across critical areas of service delivery, (i.e. Health, social grants, waiting time for pension, housing, mining applications, and water use license); Establish baseline on prioritized indicators |  |  |

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Service delivery quality and access | Value for money % improvement in the unit costs of services | To be determined | 100% implementation of competitive unit costs for services and products | Establish baseline unit costs for key drivers of government expenditure. Standardize unit costs of key cost drivers, (catering, stationery, medicines/drugs, construction) |  |  |
|  |  |  |  | Review and realignment of expenditure to achieve outcomes |  |  |
|  | Access % reduction of average distance travelled by citizens to access government services | To be determined | Establish at least 2 fully operational Thusong centres per municipality by 2014 | Establish 3 New Thusong Service Centres in the Province |  |  |
|  | Ease of access to government service through integrated platforms and channels | To be determined | Integrated Access strategy developed and implemented E-governance framework developed and implemented | Integrated access strategy for the Province developed. E-governance framework approved by Exco. |  |  |

# 3.  OUTPUT 2 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS

Output 2: Human Resource Management and Development

Output 2 Problem Statement

- An Efficient, effective and performance-oriented state machinery depends on the availability of human resources with requisite skills and competencies to achieve desired results. Equally, it requires effective management of performance and discipline to ensure compliance with policy prescripts and effective human resource systems and practices

- One of the major constraints to accelerated service delivery has been the government’s inability to attract and retain sufficient numbers of skilled people. Inadequate training and development to improve skills in critical areas of government work remains a challenge.

- Inefficiencies in the management of human resource administrative processes continue to undermine the overall capacity of the state to respond to service delivery needs of communities. These include:

  - High vacancy rates in critical areas;

  - Delays in the appointment process;

  - Delays in the finalization of disciplinary cases;

  - Non-assessment of managers, senior managers in particular.

- Non implementation of Auditor General’s (AG) findings on HR matters

High Level Interventions

- Ensure all Senior Managers including HoDs sign their PAs within the prescribed period;

- All Senior Managers, HoDs, DDGs and Municipal Managers are assessed twice per year as per SMS Handbook;

- Filling of all funded vacant posts within 4 months

- Reduce period it takes to fill a post

- Standardize application of human resource policies and ensure uniform compliance

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| HR management and development | % of senior managers signed performance agreements (PA) | 95% of senior managers including Municipal Managers signed PAs | 100% of senior managers signing performance agreements | 100% senior managers including Municipal Managers signing performance agreements within the prescribed period |  |  |
|  | % of senior managers assessed including Municipal Managers and DDGs | 83% of Accounting Officers and 48% of Municipal Managers assessed | Assessment of Accounting Officers, Municipal Managers and DDGs twice per year as per SMS Handbook | 100% Accounting Officers assessed and poor performance dealt with in terms of the prescripts |  |  |
|  | Period taken to fill a vacancy | 8 Months on average | Fill all funded vacant posts filled within 2 months | Fill all funded vacant posts within 4 months |  |  |
|  | % of reduction of vacancy rate | 35% vacancy rate across the Provincial administration | Reduce vacancy rate by 30% | Reduce vacancy rate by 10% |  |  |

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| HR management and development | Time spent to finalise disciplinary processes | 12 months | Finalize all disciplinary processes within 2 months | 3 months |  |  |
|  | Qualitative and quantitative improvement in the extent and depth of the skills levels of public servants | 90% SMS member trained on key managerial competencies. 50% Middle Managers (MMS) trained on key managerial competencies. | 80% competent and skilled work force (SMS level). 50% competent and skilled work force (MMS level). | Determine Methodology to measure extent and depth of skills levels within the public service. Implement training and development interventions based on the MMS Skills Audit. |  |  |
|  |  | Some Departments do not comply to skill development act | 3% dedicated to scarce and critical skills | Ensure 1% of salary bill is dedicated to skills development |  |  |

# 4.  OUTPUT 3 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS

Output 3: Business processes, systems, decision rights and accountability management

Output 3 Problem Statement

- Central to unlocking speed, efficiencies and effectiveness in large bureaucracies such as the Department of Health, Education, and Public Works, Roads and Transport is ensuring that accountability and decision rights are responsibly delegated so that appropriate decisions are taken at the right levels.

- Evidence shows that over-centralized powers impact negatively on service delivery as long chains of approval processes delay the actual implementation of key decisions.

- Decision-making at all levels should be supported by effective business processes and appropriate information technology systems, including procurement systems. Currently, transversal systems are not regularly updated and utilized as decision-support tools.

- Non adherence to supply chain management prescripts in terms of Bid processes, contract management and payments also impacts negatively on service delivery. The integrity of supply chain management processes should be maintained to eliminate human intrusion and conflicts of interest.

Output 3 Problem Statement (continues)

- Accountability for performance and the utilization of public finances is a seminal feature that defines an efficient, effective and development-oriented public service.  Poor management and accounting for public finances by some provincial departments and municipalities in the Province remains a major challenge.

- There is a need to improve financial management skills in public institutions to improve audit outcomes and eliminate adverse audit opinions.

High level Interventions

- Updating and integrating transversal systems for use as decision-support tools;

- Improving credibility of infrastructure procurement plans;

- Effective Implementation of appropriate delegations;

- Increase the number of departments and municipalities receiving unqualified and clean audits in line with AG’s prescripts;

- Implementation of e-procurement system;

- Acquire an electronic cabinet system (e-cabinet);

- Payment of all qualifying service providers within 30 days.

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Business processes, systems, decision rights and accountability management | Updated transversal systems | Transversal systems not fully utilized and integrated for decision making | Fully utilization of transversal systems to support decision making | Standardize and update secondary data on all transversal systems |  |  |
|  | SCM including procurement % improvement in SCM processes and turnaround times | Non adherence to SCM prescripts - Bid processes, contract Management and payments. In certain areas the 30 day period is not adhered to. | 100% compliance E-procurement system implemented by all departments Qualifying service providers paid within 30 days | 100% compliance Pilot e-procurement system with 4 Departments. Qualifying service providers paid within 30 days. |  |  |
|  | Improved infrastructure planning | Fragmented infrastructure planning and procurement | Infrastructure plans and procurement finalized prior to year of implementation | Infrastructure committee in place. Infrastructure procurement for 2011/12 finalized by February 2011 |  |  |

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Business processes, systems, decision rights and accountability management | Delegation and decision rights Number of departments with appropriate financial, human resource and administrative delegations in place | Insufficient delegations in certain areas | All departments have appropriate delegations | Determine and implement appropriate levels of delegation in all departments |  |  |
|  | Financial Management % increase in Departments receiving clean audits | 15% departments and entities received clean audits in 2009/10. 2 departments received qualified audits in 09/10 | 100% clean audit reports across provincial departments and municipalities | 38% departments and public entities receive clean audits 100% departments and public entities receive unqualified audits |  |  |
|  | 43 % municipalities received clean audits in 2008/09 |  | 60% municipalities receive clean audits | 43 % municipalities received clean audits in 2008/09 |  |  |

# 5.  OUTPUT 4 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS

Output 4: Tackling corruption in Public Service

Output 4 Problem Statement

- There is a general perception of corruption in the public service as a result of some individuals within the public service who break the law by utilizing public resources for personal gain and self-interest. Media reports continue to cast the image of the Province in a light that perpetuates the perception of a ‘corrupt’ Province. This issue must be dealt with head-on;

- Key to reversing public perception is showing ruthless decisiveness in dealing with cases of corruption where they are detected;

- The Province needs to enhance advocacy, awareness and knowledge about measures to combat fraud and corruption;

- Risk management and fraud prevention capacities within departments and municipalities are inadequate to trigger early warning signs;

- Management of the security function is poorly coordinated;

- Leakage of confidential state information undermines the integrity of the state.

High Level Interventions

- Finalization and Implementation of the Provincial Anti-Corruption  Strategy;

- Building institutional capacity for risk management and anti-corruption within departments and municipalities;

- Verification of financial declarations and background checks for SMS members and officials within SCM and Finance;

- Enhance government communication on anti-corruption programmes;

- Establish a database of compliance documents;

- Centralization of security functions within the Office of the Premier.

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Tackling corruption in Public Service | % Improvement in the corruption perception index | To be determined | Reduce perception on corruption as per baseline | Establish baseline for corruption perception index in the Province. Develop and implement action plans to address perception of corruption in the Province | 2 206 | 923 |
| Establish risk management and anti-corruption capacity in all departments and municipalities | Anti-corruption and risk management capacity established | Draft Anti-corruption strategy in place | Anti-corruption strategy fully implemented | Establish Provincial Anti-corruption Forum. Provincial Anti-corruption Strategy finalized and approved by EXCO |  |  |
| Enforcement monitoring and evaluation measures | Electronic system established | Inadequate information management system | Electronic system fully functional and data used for decision making | Develop electronic system to capture financial disclosures and other corruption data |  |  |

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Security management | Integrated security management across the provincial government | Coordination of security function currently fragmented | Centralized security management function within the Office of the Premier | Development of an integrated provincial security management plan | 1 419 | 126 |
|  |  | Reduction in the leakage of confidential and classified information | Management of confidential state information inadequate | 100% compliance with security standards throughout the Province, including local government |  |  |

# 6.  OUTPUT 5 PROBLEM STATEMENT AND HIGH LEVEL INTERVENTIONS

Output 5: Enhancing public participation

Output 5 Problem Statement

- An important measure of democratic governance is the ability to strengthen systems of public participation, transparency, integrity and accountability for service delivery outcomes. Public participation is essential to foster communities’ ownership of their own development and empowerment.

- Unfortunately, current structures established to enhance public participation such as ward committees, hospital boards, community development workers, community policing forums are not operating optimally.

- Communication of government programmes and feedback on issues raised by communities remain inadequate.  Accessibility of government and elected public representatives should serve the platform for regular interaction with communities on development and service delivery issues.

High Level Interventions

- Strengthen public participation structures and processes at all levels of governance

- Establishment of the Provincial Call Centre to track, manage and respond to issues raised by communities

- Finalization and Implementation of the new Cabinet Outreach Model

| Output | Indicator/ Measure | Baseline | 5-yr Targets | 2010/11 Targets | MTEF Budget R’000 | 2010/11 Budget R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| Enhancing public participation | Number of functional governance structures | To be determined | Fully functional and resourced governance structures | Implement new measures to enhance effectiveness of community participation structures |  |  |
|  | Functional provincial call centre | Provincial issues are raised through the Presidential hotline and responses are coordinated | Fully functional Provincial Call centre | Establishment of the Provincial Call Centre | 1 892 | 1 383 |
|  | Quantity and quality of citizen input and feedback on government programmes | To be determined | New Cabinet Outreach Model fully implemented Credible system for community profiling in place | New Cabinet Outreach Model fully implemented. Effective tracking system for Cabinet commitments during repeat visits |  |  |

# 7.  KEY DELIVERY PARTNERS

| Partner | Contribution |
| --- | --- |
| GTZ | Provide technical support |
| All Provincial Departments | Policy and programme implementation |
| Municipalities | Policy implementation Roll out of Thusong Centres in the Province |
| Office of the Public Service Commission (OPSC) | Assessment of Performance Agreements |
| Department of Public Service and Administration (DPSA) | Provide Frameworks and Guidelines; |
| South African Qualification Authority | Verification of Qualifications |
| Stats-SA | Partnership on statistical information management, |
| NIA | Vetting of officials |
| SITA | Information Technology support |
| SIU | Special investigations |
| AFU | Recovery of state losses |
| SAPS | Criminal investigations entirely |

# 8.  SIGNATORIES

The following are the signatories to this Delivery Agreement and hence commit themselves towards achieving the desired outcomes and outputs of this document.

SIGNATURE:    __________________________________    DATE: ______________2010

HON. DD MABUZA, PREMIER, OFFICE OF THE PREMIER

SIGNATURE:    __________________________________    DATE: ______________2010

MR MB MASUKU, MPL, MEMBER OF EXECUTIVE COUNCIL FOR COOPERATIVE GOVERNANCE AND TRADITIONAL AFFAIRS

SIGNATURE:    __________________________________    DATE: ______________2010

MS MNS MANANA, MPL, MEMBER OF EXECUTIVE COUNCIL FOR CULTURE, SPORT AND RECREATION

SIGNATURE:    __________________________________    DATE: ______________2010

MRS YN PHOSA, MPL, MEMBER OF EXECUTIVE COUNCIL FOR FINANCE