| OUTPUTS AND OUTPUT DEFINITIONS | NATIONAL DELIVERABLES | PROVINCIAL BASELINE | PROVINCIAL ACTIVITIES | ACTIONS: COGTA & Partners | Provincial Target 2010/11 | Proposed Target 2011/12 (subject to budget approval) | Proposed Target 2012/13 (subject to budget approval) | Proposed Target 2013/14 (subject to budget approval) | INDICATOR | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT 1: Implement a differentiated approach to municipal financing, planning and support | Simplified IDP’s, focusing on the delivery of a set of 10 critical municipal services | All 21 Councils adopted IDPs as approved by MEC by 31 July 2010 | Implement a focused intervention to support the development of IDPs that are simplified to focus on planning for the delivery of a set of 10 critical municipal services in smaller municipalities Initiate and support the Review of powers and functions undertaken | COGTA Support implementation of revised simplified and differentiated IDPs to ensure more effective planning and intergovernmental cooperation | 21 municipalities with realistic IDPs | Implement the revised IDP Framework Guide in 100% of selected smaller municipalities. | Implement the revised IDP Framework Guide in 100% of selected smaller municipalities. | Implement the revised IDP Framework Guide in 100% of selected smaller municipalities. | Number of smaller municipalities where revised IDP framework guide has been rolled out | Resources available |
|  |  |  |  | All Provincial Departments Ensure participation at strategic level in development and finalisation of sector plans during IDP review processes |  | All sector plans integrated into municipal IDPs | All sector plans integrated into municipal IDPs | All sector plans integrated into municipal IDPs | Number of IDPs with 100% compliance to sector plan integration | Resources available |
|  |  |  |  | Municipalities: Implement the revised IDP framework guide |  | The 100% of selected smaller municipalities fully effecting the revised IDP Framework | The 100% of selected smaller municipalities fully effecting the revised IDP Framework | 100% of selected smaller municipalities fully effecting the revised IDP Framework | Nr of municipalities fully implementing the revised IDP Framework | Municipalities to indicate resources |
| OUTPUT 1: (cont) | Simple Revenue Plans developed and implemented | 10 municipalities identified for financial turnaround support Hands-on support availed to Thaba Chweu & Lekwa Support additional to S139 intervention provided to Thembisile Hani, Emalahleni, Mkhondo, Thaba Chweu | Supported IDPs through a simple revenue plan to better manage costs and enhance management of revenue. Implement debt collection systems and improve the billing systems | COGTA & Provincial Treasury: Implement simple revenue plan in 100% smaller municipalities COGTA Roll-out a support programme for billing systems and cost recovery | 10 municipalities identified for financial turnaround support 4 Municipalities | Manage the implementation of the revised simple revenue plan in 100% of selected smaller municipalities 6 municipalities. | Manage the implementation of the revised simple revenue plan in 100% of selected smaller municipalities. 6 municipalities | Manage the implementation of the revised simple revenue plan in 100% of selected smaller municipalities. 6 municipalities | Number of smaller municipalities where simplified revenue plans have been rolled out 18 local municipalities | Resources available |
|  |  |  |  | Municipalities: Implement the simplified revenue plan |  | 100% of targeted smaller municipalities roll-out the revised simple revenue plan | 100% of targeted smaller municipalities roll-out the revised simple revenue plan | 100% of targeted smaller municipalities roll-out the revised simple revenue plan | Nr of municipalities that implement the simple revenue plan. | Municipalities to indicate resources |
|  | The six (6) critical posts of Municipal Manager (MM), Town Planner, Chief Financial Officer, Engineer/ technical services, HR manager and Communications manager are filled by competent and suitably qualified individuals | 95 of 121 (79%) of posts filled. MMs: 15 of 21 filled Vacancies: 6 (MLM, TCLM, MKLM, NLM, THLM, LLM) Suspensions:3 (BLM, ELM, ALLM) | Filling of critical posts improve from 80% to 100% Roll-out of the National Capacity Building Programme, Municipal Leadership and Development Programme | COGTA and SALGA: Audit of top six (6) critical posts in municipalities | 100% filled and all top 6 positions assessed | Quarterly and annual monitoring of 6 critical posts Implement the support plan to assist municipalities to fill the critical posts | Quarterly and annual monitoring of 6 critical posts Implement the support plan to assist municipalities to fill the critical posts | Quarterly and annual monitoring of 6 critical posts Implement the support plan to assist municipalities to fill the critical posts Review the support plan | Regular compilation and submission to DCoG of quality monitoring reports Number of municipalities where the critical posts are filled | COGTA: Resources available |
|  |  |  |  | Municipalities: Fill top six critical posts of Municipal Manager (MM), Town Planner, Chief Financial Officer, Engineer/ technical services, HR manager and Communications manager with competent and suitably qualified individuals | Develop a plan to ensure that the top six critical posts are filled within 90 days | Fill vacant critical posts within a 90 day period | Fill vacant critical posts within a 90 day period | Fill vacant critical posts within a 90 day period | % of municipalities in which top posts are filled Vacant positions for the top six critical posts are filled within 90 days. | Municipalities to indicate resources |
| OUTPUT 1: (cont) | Performance contract of the Municipal Manager is crisp and concise and has key LGTAS performance indicators | Employment contracts: 106/121 signed (87,6%) PAs: 101/121 signed (83%) | Support the implementation of functional performance management system at municipal level | COGTA: Support & monitor the implementation of guidelines to ensure that the Performance contracts of the Municipal Managers includes key LGTAS performance indicators | Signed PAs of Section 56 and 57 managers to increase from 86% to 100% | Support and monitor the implementation of guidelines on Performance Contracts | Support and monitor the implementation of guidelines on Performance Contracts | Support and monitor the implementation of guidelines on Performance Contracts Review the guidelines on Performance Contracts for Municipal Managers | Number of municipalities implementing the guidelines on performance contracts for Municipal manager that includes key LGTAS performance indicators | Resources available |
|  |  |  |  | Municipalities: Sign performance contracts with Section 56 and 57 managers that contain key LGTAS Performance Indicators | All Section 56 and 57 managers have signed annual PA by 31 August, and new appointees within 3 months of signing employment contract | All Section 56 and 57 managers have signed annual PA by 31 August, and new appointees within 3 months of signing employment contract | All Section 56 and 57 managers have signed annual PA by 31 August, and new appointees within 3 months of signing employment contract | All Section 56 and 57 managers have signed annual PA by 31 August, and new appointees within 3 months of signing employment contract | Number of performance contracts for Section 56 and 57 managers that includes key LGTAS performance indicators | Municipalities to indicate resources |
|  | Top six critical posts in municipalities are not filled by elected officials of any political party | None | Support municipalities in filling the six critical positions with suitably qualified persons. | COGTA will support and monitor the implementation of the framework, regulated HR systems and procedures | COGTA to participate in development of professionalization framework | Implement the professionalization framework in 100% of municipalities Implementation and monitoring compliance with the enacted legislation | Implement the professionalization framework in 100% of municipalities Implementation and monitoring compliance with the legislation | Implement the professionalization framework in 100% of municipalities Implementation and monitoring compliance with the legislation | Professionalization Framework on LG developed and adopted by 31 March 2011 Number of municipalities complying with the framework | Resources available |

| OUTPUTS AND OUTPUT DEFINITIONS | NATIONAL DELIVERABLES | PROVINCIAL BASELINE | PROVINCIAL ACTIVITIES | ACTIONS: COGTA & Partners | Provincial Target 2010/11 | Proposed Target 2011/12 (subject to budget approval) | Proposed Target 2012/13 (subject to budget approval) | Proposed Target 2013/14 (subject to budget approval) | INDICATOR | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT 2 Improving Access to Basic Services. | Bulk Infrastructure Fund (BIF) | None | Review the LGES (Equitable Share) | COGTA Monitor and report on the projects implemented through the BIF. | Develop a comprehensive programme proposal to establish and implement a provincial BIF by December 2010 | Roll-out and monitor the implementation of the BIF. | Roll-out and monitor the implementation of the BIF. | Roll-out and monitor the implementation of the BIF. Review the implementation of the BIF | Number of bulk infrastructure projects funded through the Bulk Infrastructure Fund (BIF) | COGTA: Resources available |
|  |  | None | Unlock delivery of reticulation services | Comprehensive Infrastructure Planning and project implementation support Spatial mapping GIS Technical Support to Municipalities | Municipalities supported through set agreements to improve service delivery in all district spaces Municipalities audited on MIG project locations by 31 March 2011 | 100% of Districts supported with comprehensive infrastructure planning 50% of all MIG projects mapped on the GIS | 100% of Districts supported with comprehensive infrastructure planning 80% of all MIG projects mapped on the GIS | 100% of Districts supported with comprehensive infrastructure planning 100% of all MIG projects mapped on the GIS | Nr of districts with agreed, signed off service delivery implementation plans catering for their MTAS’s by target dates | COGTA: Resources available |
|  |  | None | Procure well located land | Department of Public Works & Department of Rural Development and Land Reform: Identify and fast track the procurement of well located land for municipal development | Prepare a plan to identify and fast track the procurement of well located land for municipal development by December 2010 | Implement the plan identify and fast track the procurement of well located land | Implement the plan identify and fast track the procurement of well located land | Implement the plan identify and fast track the procurement of well located land | Number of municipalities supported with the fast tracking of the procurement of well located land | Department of Public Works & Department of Rural Development and Land Reform to indicate resources |
|  |  |  |  | COGTA Facilitate the release of land in collaboration with Traditional Leadership Structures and the Department of Rural Development and Land Reform | Prepare a plan to identify and facilitate acquisition of well located land for municipal development in collaboration with traditional leadership structures by November 2010 | Implement the plan identify and fast track the procurement of well located land | Implement the plan identify and fast track the procurement of well located land | Implement the plan identify and fast track the procurement of well located land | Number of municipalities supported with the acquisition of well located land in collaboration with traditional leadership structures | COGTA, municipalities, Land Reform and Public Works to indicate resource availability |
| OUTPUT 2 (cont) | Bulk Infrastructure Fund (BIF) | None | Align relevant grants and infrastructure projects | COGTA, DWA and Human Settlement Align Provincial Infrastructure Grants with housing projects and grants | Prepare a plan to align the relevant grants and infrastructure programmes and housing programme | Implement the grant and infrastructure alignment plan | Implement the grant and infrastructure alignment plan | Implement the grant and infrastructure alignment plan | Number of provincial and municipal housing projects that reflect the alignment of the various infrastructure & grant programmes | COGTA: Resources available HS and DWA to indicate |
|  |  | None | Align Provincial Infrastructure Grants and Municipal Infrastructure Grants (MIG) with housing projects and grants. | COGTA & HS: Improve Grant Co-ordination – MIG, MSIG etc. | Finalization and Communication of the Macro Grant Co-ordination Framework to all municipalities by 31 March 2011 | Implementation of the Macro Grant Co-ordination Framework | Implementation of the Macro Grant Co-ordination Framework | Implementation of the Macro Grant Co-ordination Framework | Number of municipalities to which the Macro-grant Co-ordination Framework have been implemented | COGTA: Resources available HS to indicate |
|  |  | None | Upgrade & rehabilitate bulk infrastructure. Infrastructure asset register finalised. Infrastructure asset management plans finalised. Provincial basic services infrastructure framework developed. Effective and efficient use of water and electricity. | COGTA: Support National Municipal Infrastructure Audit | Provincial State of Infrastructure Report with Intervention Plan (inclusive of budget) by 31 March 2011 | Implementation and monitoring of the Intervention Plan | Implementation and monitoring of the Intervention Plan | Implementation and monitoring of the Intervention Plan Review of the Implementation Plan | Report on condition / state of infrastructure by target date Progress in implementing the Intervention Plan against key indicators | COGTA: Resources available |
|  |  |  |  | COGTA & HS: Support municipalities to upgrade and rehabilitate bulk infrastructure | Develop a plan to support municipalities to upgrade and rehabilitate bulk infrastructure by December 2010 | Implement and monitor the plan to support municipalities to upgrade and rehabilitate bulk infrastructure | Implement and monitor the plan to support municipalities to upgrade and rehabilitate bulk infrastructure | Implement and monitor the plan to support municipalities to upgrade and rehabilitate bulk infrastructure | Number of municipalities and upgrading and rehabilitation projects supported | COGTA: Resources available HS to indicate |
|  |  |  |  | Municipalities: Upgrade and rehabilitate bulk infrastructure | Develop a plan to upgrade and rehabilitate bulk infrastructure by September 2010 | Implement and monitor the plan to upgrade and rehabilitate bulk infrastructure | Implement and monitor the plan to upgrade and rehabilitate bulk infrastructure | Implement and monitor the plan to upgrade and rehabilitate bulk infrastructure | Number of municipal upgrading and rehabilitation projects | Municipalities to indicate resources |
| OUTPUT 2 (cont) | Special purpose public Vehicle (SPV) to address infrastructure development | None | Establish a provincial special purpose vehicle for municipal infrastructure to assist in mobilizing private sector infrastructure funding for municipalities and also to support the planning and expenditure of CAPEX and OPEX in municipalities. | COGTA, DEDET AND PT: Support municipalities through the mobilization of private sector investment | Provincial Alternate SPV established and functional by 31 March 2011 | 6 municipalities supported with infrastructure planning, delivery and expenditure management | 10 municipalities supported with infrastructure planning, delivery and expenditure management | All category B3 and B4 municipalities supported with infrastructure planning, delivery and expenditure management | Number of municipalities supported with infrastructure planning and expenditure management | COGTA: resources available |
|  |  |  |  | COGTA, DEDET and PT Promotion and Facilitation of Municipal Service Partnerships (MSPs) | Promotion and facilitation of MSP’s in 4 targeted municipalities by 31 March 2011 Development of a plan to support a targeted number of municipalities with MSPs by November 2010 | 6 of targeted municipalities supported with MSPs | 6 of targeted municipalities supported with MSPs | 4 of targeted municipalities supported with MSPs | Municipal Service Partnerships (MSPs) facilitated in identified municipalities by target date | COGTA: Resources available |
|  | Special purpose public Vehicle (SPV) to address infrastructure development (cont) |  | Establish a special purpose vehicle for municipal infrastructure to assist in mobilizing private sector infrastructure funding for municipalities (cont) | Department of Health: Promotion and facilitation of Municipal Service Partnerships for Municipal Health Services | Development of a plan to support a targeted number of municipalities with MSPs for Municipal Health Services by November 2010 | 30% of targeted municipalities supported with MSPs | 70% of targeted municipalities supported with MSPs | 100% of targeted municipalities supported with MSPs | Number of Municipalities where MSP’s for Municipal Health Services have been implemented | DoH to indicate |
|  |  | None |  | COGTA and DEDET Adopt-a-municipality: MOUs signed between business and SOEs and municipalities on LED related infrastructure projects | Memorandums of understanding with 5 municipalities by 31 March 2011 Development of a plan to facilitate a number of MOUs in a targeted number of municipalities & SOEs / businesses with LED-related projects by November 2010 | 6 of targeted municipalities supported with MOUs | 3 of targeted municipalities supported with MOUs | 4 of targeted municipalities supported with MOUs | Number of municipalities which have signed MOUs for LED including infrastructure related plans that are business and SOEs driven | COGTA: Resources available |
| OUTPUT 2 (cont) | Increased household access to water from 92% to 100% | 91,3% | Monitoring and Evaluation System on Basic Delivery Verification exercise to be conducted on access to basic services by COGTA, STATSA AND OTP | COGTA, HS AND DWA Roll-out of MIG water and sanitation projects | 95% households with access to water | 96% households with access to water | 98% households with access to water | 100% households with access to water | % of households with access to basic water. | COGTA: resources available |
|  |  |  |  | COGTA & HS, DWA Support municipalities to increase household access to water | Develop a plan to support municipalities to increase household access to water by December 2010 | Implement and monitor the plan to support municipalities to increase household access to water | Implement and monitor the plan to support municipalities to increase household access to water | Implement and review the plan to support municipalities to increase household access to water |  | COGTA: Resources available HS, DWA to indicate |
|  |  |  |  | Municipalities: Increase household access to water services | All targeted municipalities with water backlogs have plans to meet their targets | 30% of identified households have access to water in targeted municipalities | 70% of identified households have access to water in targeted municipalities | 100% households with access to water |  | Municipalities to indicate resources |
| OUTPUT 2 (cont) | Increased household access to water from 92% to 100% (cont) | 91,3% | Maintenance and supply availability of bulk water infrastructure Maintenance and supply availability of bulk water infrastructure (cont) | Department of Water Affairs Reduce backlog on rehabilitation/refurbishment of the national water resources infrastructure | Finalise plan to reduce rehabilitation backlogs in provincial water infrastructure | Implement plan to reduce rehabilitation backlogs in national water infrastructure against set targets | Implement plan to reduce rehabilitation backlogs in national water infrastructure against set targets | 1. From 15% of asset value to 10% of asset value by 2014 2. Implement 7 of the proposed water augmentation schemes. | % reduction of asset value for refurbishment backlog | Department of Water Affairs: to indicate resources |
|  |  |  |  | Department of Water Affairs: Reduce unaccounted-for bulk water and water losses from distribution networks | Finalise plan to reduce unaccounted bulk water and water loss | Implement plan to reduce unaccounted bulk water against set targets | Implement plan to reduce unaccounted bulk water against set targets | From approximately 30% of supply to 15%. | % unaccounted for bulk water and water loss | Department of Water Affairs: to indicate resources |
|  |  |  | Improve rural services and sustainable livelihoods | Department of Rural Development and Land Reform Support the eradication of backlogs of household access to water in rural areas | Finalise a support plan to ensure increased household access to water in rural areas | Implement the support plan to ensure increased household access to water in rural areas against set targets | Implement the support plan to ensure increased household access to water in rural areas against set targets | The proportion of households with clean water rises from 74% to 90%. | The proportion of rural households with clean water | Department of Rural Development and Land Reform: to indicate resources |
|  | Increased household access to sanitation from 69% to 100% | 53,9% | Improve the capacity of WTW treatment plan and ensure improved results with respect to the green drop criteria | Department of Water Affairs and the Environment: To improve current capacity of sewage and wastewater treatment plants | Finalise a national plan to support the upgrading / rehabilitation of sewage and wastewater treatment works and plants | Implement the national plan to support the upgrading / rehabilitation of sewage and wastewater treatment works and plants against set indicators & targets | Implement the national plan to support the upgrading / rehabilitation of sewage and wastewater treatment works and plants against set indicators & targets | 80% of sewage and wastewater treatment plants should be upgraded by 2015 and the percentage of wastewater treatment plants meeting water quality standards should be increased from 40% to 80% by 2014. | % of sewage and wastewater treatment plants that have been upgraded % of wastewater treatment plants meeting the water quality standards | Department of Water Affairs: to indicate resources |
|  |  |  | Targeted support to municipalities in the roll-out of sanitation infrastructure | COGTA, DWA, HS Roll-out of MIG water and sanitation projects | 65% households with access to sanitation | 85% households with access to sanitation | 95% households with access to sanitation | 100% households with access to sanitation | % of households with access to sanitation. | DCoG: resources available allocated |
| OUTPUT 2 (cont) |  |  | Provincial plan crafted and implemented. | COGTA & HS Support municipalities to increase household access to sanitation | Develop a plan to support municipalities to increase household access to sanitation by December 2010 | Implement and monitor the plan to support municipalities to increase household access to sanitation | Implement and monitor the plan to support municipalities to increase household access to sanitation | Implement and review the plan to support municipalities to increase household access to sanitation | % of households with access to sanitation. | COGTA and HS to indicate |
|  | Increased household access to sanitation from 69% to 100% | 53,9% | Support provided to municipalities to craft their differentiated plans. | Municipalities: Provide households with sanitation services | All targeted municipalities with sanitation backlogs have plans to meet their targets | 30% of identified households have access to sanitation in targeted municipalities | 70% of identified households have access to sanitation in targeted municipalities | 100% of households have access to sanitation |  | Municipalities to indicate resources |
|  |  |  | Support implementation plans finalized and implemented | Department of Water Affairs AND HS: Support the increase of household access to sanitation from 69% to 100% | Finalise a support plan to ensure increased household access to sanitation | Implement the support plan to ensure increased household access to sanitation against set targets | Implement the support plan to ensure increased household access to sanitation against set targets | 100% of households have access to sanitation | Number of municipalities supported % households with access to sanitation | Department of Water Affairs: to indicate resources |
|  |  |  |  | Human Settlements Support the increase of household access to sanitation from 69% to 100% | Finalise a support plan to ensure increased household access to sanitation | Implement the support plan to ensure increased household access to sanitation against set targets | Implement the support plan to ensure increased household access to sanitation against set targets | 100% of households have access to sanitation Number of municipalities supported | Number of municipalities supported % households with access to sanitation | Department of Human Settlements: to indicate resources |
|  | Increased household access to refuse removal services from 64% to 75% | 41,5% | Provincial plan crafted and implemented | DCoG & COGTA: Support accelerated refuse and waste management implementation Roll-out of MIG refuse and waste management projects | Refuse and Waste Management Coordinating structure | Implementation and monitoring of waste management plan | Implementation and monitoring of waste management plan | Implementation and monitoring of waste management plan | Refuse and Waste management coordinating structure created by target date | DCoG: resources available & allocated COGTA to indicate |
|  |  |  |  | Municipalities Provide households with refuse removal services | All targeted municipalities with waste management & refuse removal backlogs have plans to meet their targets | 30% of identified households have access to waste management & refuse removal services in targeted municipalities | 70% of identified households have access to waste management & refuse removal services in targeted municipalities | 100% of identified households have access to waste management & refuse removal services in targeted municipalities | % of households provided with refuse removal services. | Municipalities to indicate resources |
| OUTPUT 2 (cont) | Increased household access to refuse removal services from 64% to 75% (cont) | 41,5% | Provincial electrification and support plan implemented. | COGTA, DEDET, HS: Support municipalities to increase household access to waste management & refuse removal services | Develop a plan to support municipalities to increase household access to waste management & refuse removal services by December 2010 | Implement and monitor the plan to support municipalities to increase household access to waste management & refuse removal services | Implement and monitor the plan to support municipalities to increase household access to waste management & refuse removal services | Implement and review the plan to support municipalities to increase household access to waste management & refuse removal services | % of households with access to waste management & refuse removal services | COGTA, DEDET, HS Indicate resources |
|  |  |  | Sustainable environmental management | Department of Environmental Affairs: Support municipalities to have waste management plans to ensure waste minimization, improved collection and disposal and recycling | National support programme aimed at municipalities to have waste management plans | Implementation and monitoring of national support programme aimed at municipalities to have waste management plans against set targets | Implementation and monitoring of national support programme aimed at municipalities to have waste management plans against set targets | Implementation and review of national support programme aimed at municipalities to have waste management plans against set targets | % of households with basic waste collection and disposal facilities Number of municipalities with waste management plans | Department of Environmental Affairs: to indicate resources |
|  | Increased household access to electricity from 81% to 92% | 81,7% | Provincial electrification plan and support finalized | COGTA, ESKOM, Energy Support accelerated household access to basic electricity and Free Basic Energy in a financial sustainable manner | Provincial support plan to ensure increased access to basic electricity 85 % households have access to electricity | Implementation and monitoring of provincial support plan to ensure increased access to basic electricity 85 % households have access to electricity | Implementation and monitoring of provincial support plan to ensure increased access to basic electricity 90% households have access to electricity | Implementation and monitoring of provincial support plan to ensure increased access to basic electricity 92% households have access to electricity | % of households with access to electricity | ENERGY AND ESKOM Indicate resources |
|  |  |  |  | Municipalities Provide households with access to electricity | All targeted municipalities with electricity backlogs have plans to meet their targets | 30% of identified households have access to electricity in targeted municipalities | 70% of identified households have access to electricity in targeted municipalities | 100% of identified households have access to electricity in targeted municipalities |  | Municipalities to indicate |
| OUTPUT 2 (cont) | Increased household access to electricity from 81% to 92% (cont) | 81,7% | Provincial electrification plan and support finalized | COGTA Support municipalities to provide households with access to electricity | Develop a plan to support municipalities to increase household access to electricity by December 2010 | Implement and monitor the plan to support municipalities to increase household access to electricity | Implement and monitor the plan to support municipalities to increase household access to electricity | Implement and review the plan to support municipalities to increase household access to electricity | % of households with access to electricity | COGTA to indicate |
|  |  |  |  | Department of Energy: Support accelerated household access to basic electricity and Free Basic Energy in a financial sustainable manner | National support plan to ensure increased access to basic electricity 85 % households have access to electricity | Implementation and monitoring of national support plan to ensure increased access to basic electricity 87 % households have access to electricity | Implementation and monitoring of national support plan to ensure increased access to basic electricity 90% households have access to electricity | Implementation and monitoring of national support plan to ensure increased access to basic electricity 92% households have access to electricity |  | Department of Energy to indicate |
|  |  |  | Improve rural services and sustainable livelihoods | Eskom / EDI/REDS: Ensure reliable generation, transmission and distribution of electricity Support accelerated household access to basic electricity and Free Basic Energy in financial sustainable manner | National support plan to ensure increased access to basic electricity 85 % households have access to electricity | Implementation and monitoring of national support plan to ensure increased access to basic electricity 87 % households have access to electricity | Implementation and monitoring of national support plan to ensure increased access to basic electricity 90% households have access to electricity | Implementation and monitoring of national support plan to ensure increased access to basic electricity 92% households have access to electricity | % of households with access to electricity | Eskom / EDI/REDS to indicate |
| OUTPUT 2 (cont) | Increased household access to electricity from 81% to 92% (cont) | 81,7% | Improve rural services and sustainable livelihoods (cont) | Department of Rural Development and Land Reform; DARDLA Increase access to electricity for households in rural municipalities | Finalise a support plan to ensure increased household access to electricity in rural areas | Implement the support plan to ensure increased household access to electricity in rural areas against set targets | Implement the support plan to ensure increased household access to electricity in rural areas against set targets | The proportion of households with access to improved electricity rises 92% | The proportion of households with access to improved electricity | Rural Development and Land Reform & DARDLA to indicate |

| OUTPUTS AND OUTPUT DEFINITIONS | NATIONAL DELIVERABLES | PROVINCIAL BASELINE | PROVINCIAL ACTIVITIES | ACTIONS: COGTA & Partners | Provincial Target 2010/11 | Proposed Target 2011/12 (subject to budget approval) | Proposed Target 2012/13 (subject to budget approval) | Proposed Target 2013/14 (subject to budget approval) | INDICATOR | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT 3: Implementation of the Community Work Programme (CWP) | Create 4,5 million work opportunities through EPWP (CWP to contribute 237,000 job opportunities to this target) | None | Facilitate the roll-out of CWP in at least 2 wards per municipality | DCoG, COGTA & municipalities Implement the CWP in at least 2 wards per local municipality | Finalise a provincial plan to ensure the roll-out of the CWP in at least 2 wards per local municipality | Implement and monitor the provincial plan to ensure the roll-out of the CWP in at least 2 wards per identified local municipality | Implement and monitor the provincial plan to ensure the roll-out of the CWP in at least 2 wards per identified local municipality | Implement and monitor the provincial plan to ensure the roll-out of the CWP in at least 2 wards per identified local municipality | Number of wards per municipality implementing the CWP | DCoG: resources available allocated COGTA to indicate Municipalities to indicate resources |
|  |  |  | Support job creation through functional cooperatives | DCoG, COGTA, DEDET & municipalities Utilise the CWP to support the establishment of cooperatives in each ward | Finalise a plan to ensure that 30% of all job opportunities of the CWP must be associated with functional cooperatives at a ward level Develop a plan to establish cooperatives in each ward | 10% of all job opportunities of the CWP must be associated with functional cooperatives at a ward level Implement and monitor the plan to establish cooperatives in each ward | 20% of all job opportunities of the CWP must be associated with functional cooperatives at a ward level Implement and monitor the plan to establish cooperatives in each ward | 30% of all job opportunities of the CWP must be associated with functional cooperatives at a ward level Implement and review the plan to establish cooperatives in each ward | % of all job opportunities of the CWP must be associated with functional cooperatives at a ward level | DCoG: resources available allocated DEDET to indicate COGTA to indicate Municipalities to indicate resources |
|  |  |  |  | Department of Agriculture & DARDLA Organize small farmers in producer associations or marketing cooperatives | Develop a plan to organize small farmers in producer associations or marketing cooperatives | Implement and monitor the plan to organize small farmers in producer associations or marketing cooperatives | Implement and monitor the plan to organize small farmers in producer associations or marketing cooperatives | Implement and monitor the plan to organize small farmers in producer associations or marketing cooperatives | % of small farmers organised in marketing cooperatives | Department of Agriculture & DARDLA to indicate |
|  |  |  | Identify and create useful work” opportunities | DCoG, COGTA & Municipalities Create work opportunities through CWP | 4,000 work opportunities created by 31 March 2011 (two wards per selected Municipality) | 10,000 work opportunities created | 30,000 work opportunities created | 36,000 work opportunities created | Number of useful work opportunities created by target date | DCoG: resources available allocated COGTA to indicate Municipalities to indicate |
| OUTPUT 3: (CONT) | Create 4,5 million work opportunities through EPWP (CWP to contribute 237,000 job opportunities to this target) (cont) | None | Integrated provincial job creation strategy finalised. Rural economic development imperatives integrated into the LED strategies. Strengthen labour absorption measures through service delivery provision. | COGTA Support the role of traditional leadership structures in facilitating job opportunities through the CWP | Develop a plan to define the role of traditional leadership structures in facilitating job opportunities through the CWP | Implement and monitor the plan to define the role of traditional leadership structures in facilitating job opportunities through the CWP | Implement and monitor the plan to define the role of traditional leadership structures in facilitating job opportunities through the CWP | Implement and review the plan to define the role of traditional leadership structures in facilitating job opportunities through the CWP | Number of CWP useful work opportunities facilitated by traditional leadership structures | COGTA: Resources available |
|  |  |  |  | Department of Rural Development and Land Reform; DARDLA Ensure that unemployment falls from 73.4 % to 60% in the current poverty nodes | Develop a plan to ensure that unemployment is reduced from 73.4% to 60 % in the current poverty nodes | Implement and monitor the plan to ensure that unemployment is reduced from 73.4% to 70 % in current poverty nodes | Implement and monitor the plan to ensure that unemployment is reduced from 73.4% to 65 % in current poverty nodes | Implement and monitor the plan to ensure that unemployment is reduced from 73.4% to 60 % in current poverty nodes | % unemployment in current poverty nodes | Dept of Rural Development & DARDLA to indicate target and resources allocated |
|  |  |  |  | Department of Agriculture & DEDET/MEGA Increase jobs in agro-processing from 380 000 to 500 000, of which 60% are in rural areas, including small towns | Finalise a plan to create new job opportunities in agro-processing | Implement and monitor the plan to create new job opportunities in agro-processing | Implement and monitor the plan to create new job opportunities in agro-processing | Implement and monitor the plan to create new job opportunities in agro-processing | Nr of job opportunities created in agro-processing % of the above jobs created located in rural areas | Department of Agriculture & DEDET/MEGA to indicate |
| OUTPUT 3: (CONT) |  |  |  | Department of Agriculture DARDLA The number of smallholder farmers should rise from 200 000 to 250 000 | Finalise a plan to create new job opportunities through increasing smallholder farmers | Implement and monitor the plan to create new job opportunities through increasing smallholder farmers | Implement and monitor the plan to create new job opportunities through increasing smallholder farmers | Implement and monitor the plan to create new job opportunities through increasing smallholder farmers | Number of new work opportunities created through increasing smallholder farmers | Department of Agriculture & DARDLA to indicate |
|  | Create 4,5 million work opportunities through EPWP (CWP to contribute 237,000 job opportunities to this target) (cont) | None | Rural economic development imperatives integrated into the LED strategies. Strengthen labour absorption measures through service delivery provision. (cont) | Department of Rural Development and Land Reform & DARDLA Jobs created by Community Work Programme and EPWP in rural areas rises | Develop a plan to support the creation of EPWP & CWP job opportunities within rural municipalities | Implement and monitor the plan to support the creation of EPWP & CWP job opportunities within rural municipalities | Implement and monitor the plan to support the creation of EPWP & CWP job opportunities within rural municipalities | Implement and review the plan to support the creation of EPWP & CWP job opportunities within rural municipalities | Number of jobs created by CWP and EPWP in rural areas | Department of Rural Development and Land Reform & DARDLA to indicate |
|  |  |  |  | Department of Tourism & DEDET Jobs created through tourism in local municipalities | Develop a plan to support the creation of EPWP & CWP job opportunities linked to the tourism sector within municipalities | Implement and monitor the plan to support the creation of EPWP & CWP job opportunities linked to the tourism sector within municipalities | Implement and monitor the plan to support the creation of EPWP & CWP job opportunities linked to the tourism sector within municipalities | Implement and review the plan to support the creation of EPWP & CWP job opportunities linked to the tourism sector within municipalities | Number of jobs created through tourism in municipalities | Dept of Tourism & DEDET to indicate |
|  |  |  | Ensure alignment between the EPWP and CWP | DPWR&T Manage the EPWP and support the roll-out of the CWP | Manage the implementation of the EPWP and support the CWP to ensure that the set targets are achieved | Manage the implementation of the EPWP and support the CWP to ensure that the set targets are achieved | Manage the implementation of the EPWP and support the CWP to ensure that the set targets are achieved | Manage the implementation of the EPWP and support the CWP to ensure that the set targets are achieved 4,5 million new EPWP job opportunities created | Number of new work opportunities created | DPWRT to indicate target and resources allocated |
|  |  |  |  | Municipalities: Create jobs through MIG projects & municipal programmes | All municipalities have plans to create job opportunities through various municipal programmes with clear targets | Implementation and monitoring of plans to create job opportunities through various municipal programmes | Implementation and monitoring of plans to create job opportunities through various municipal programmes | Implementation and monitoring of plans to create job opportunities through various municipal programmes | No. of jobs created through MIG projects and municipal programmes | Municipalities to indicate resources |

| OUTPUTS AND OUTPUT DEFINITIONS | NATIONAL DELIVERABLES | PROVINCIAL BASELINE | PROVINCIAL ACTIVITIES | ACTIONS: COGTA & Partners | Provincial Target 2010/11 | Proposed Target 2011/12 (subject to budget approval) | Proposed Target 2012/13 (subject to budget approval) | Proposed Target 2013/14 (subject to budget approval) | INDICATOR | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT 4 Actions supportive of the human settlement outcomes | Increased densities in metro’s and large towns | 3 municipalities (Lekwa, Nkomazi, Msukaligwa) assisted with review and approval of SDFs | Develop & implement policy framework and guidelines for increased densities in metro’s and large towns | Department of Human Settlements: Develop a policy framework for increasing densities in large towns with COGTA with clear targets | Develop a policy framework for increasing densities in large towns with COGTA with clear targets by December 2010 COGTA Ensure that environmental, spatial challenges and plans are reflected on the IDPs | Jointly manage with COGTA the implementation of a policy framework for increasing densities in metros and large towns | Jointly manage with COGTA the implementation of a policy framework for increasing densities in metros and large towns | Jointly manage and review with COGTA the implementation of a policy framework for increasing densities in metros and large towns | Increased densities in new and existing settlements in metro’s and large towns | Dept of Human Settlements to indicate |
|  | Release of Public Land for low income and affordable housing | None | Ensure the release of public land for low income and affordable housing to support the delivery of 400 000 housing units on ‘well located land’ with a 30-40 minute journey to work and services. Provincial databank on land ownership established Formalisation and zoning of land informal settlements. | Department of Public Works & DPWRT Identification, release and expropriation of public land in municipalities for low income and affordable housing | Develop a plan to identify and release suitable public land in municipalities for low income and affordable housing | Implement the plan to identify and release suitable public land in municipalities for low income and affordable housing | Implement the plan to identify and release suitable public land in municipalities for low income and affordable housing | Implement the plan to identify and release suitable public land in municipalities for low income and affordable housing | Hectares of Public Land released for low income and affordable Housing in municipalities | Dept of Public Works to indicate resources |
|  |  |  |  | Department of Rural Development and Land Reform & DARDLA Support the identification of public land in rural municipalities for low income and affordable housing | Develop a plan to identify and release suitable public land in rural municipalities for low income and affordable housing | Implement the plan to identify and release suitable public land in rural municipalities for low income and affordable housing | Implement the plan to identify and release suitable public land in rural municipalities for low income and affordable housing | Implement the plan to identify and release suitable public land in rural municipalities for low income and affordable housing | Hectares of Public Land released for low income and affordable Housing in rural municipalities | Dept of Rural Development and Land Reform & DARDLA to indicate resources |
| OUTPUT 4 (cont) | Release of Public Land for low income and affordable housing (cont) | None |  | COGTA: Facilitate the release of well located land in traditional communal areas for residential purposes, low income and affordable housing | Develop a plan to facilitate the involvement of traditional leadership structures in the identification and release suitable public land in rural areas for low income and affordable housing | Implement the plan to facilitate the involvement of traditional leadership structures in the identification and release suitable public land in rural areas for low income and affordable housing | Develop a plan to facilitate the involvement of traditional leadership structures in the identification and release suitable public land in rural areas for low income and affordable housing | Develop a plan to facilitate the involvement of traditional leadership structures in the identification and release suitable public land in rural areas for low income and affordable housing | Hectares of Public Land released for low income and affordable housing in communal areas with the support of traditional leadership structures | COGTA: Resources available |
|  | Expanded National upgrading support programme (NUSP) & 2700 Informal Settlements formalised and upgraded | None | Support the expansion of the national upgrading support programme in all priority municipalities to facilitate the upgrading of informal settlements. (grading and rezoning) | Department of Human Settlements: Manage the expanded National upgrading support programme (NUSP) | NUSP implemented in 1 priority municipalities | NUSP implemented in 2 priority municipalities | NUSP implemented in 2 priority municipalities | NUSP implemented in 1 priority municipality 2700 Informal Settlements formalised and upgraded | Number of municipalities where the NUSP is implemented | Dept of Human Settlements to indicate resources |

| OUTPUTS AND OUTPUT DEFINITIONS | NATIONAL DELIVERABLES | PROVINCIAL BASELINE | PROVINCIAL ACTIVITIES | ACTIONS: COGTA & Partners | Provincial Target 2010/11 | Proposed Target 2011/12 (subject to budget approval) | Proposed Target 2012/13 (subject to budget approval) | Proposed Target 2013/14 (subject to budget approval) | INDICATOR | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT 5: Deepen democracy through a refined Ward Committee Model | Improved resourcing and funding of the work and activities of refined Ward Committee model | 284 out of 365 ward committees functional 81 not functional Delimitation of 37 wards published for comments Total of 402 ward committees according to new delimitations | Develop new approach for better funding of ward committees | DCoG: New funding model for ward committees developed | Ward Committees funding model developed by March 2011 | Implementation and monitoring of the functionality of funding model of ward committees | Implementation and monitoring of the functionality of funding model of ward committees | Implementation and monitoring of the functionality of funding model of ward committees | Funding model developed by target date Number of municipalities with fully functional Ward Committees implementing the new funding model Annual reports on the functionality of ward committed submitted | DCoG: resources available allocated |
|  |  |  |  | COGTA Support programme for the revised Ward Committee model developed | Support programme developed by March 2011 | Implementation of the provincial support programme for the new Ward Committee model | Implementation of the provincial support programme for the new Ward Committee model | Implementation of the provincial support programme for the new Ward Committee model | Number of municipalities supported by the provincial support programme | COGTA to indicate |
|  |  |  |  | Municipalities: Implement new model for WCs |  | New Ward Committee model implemented in at least 35% of all wards | New Ward Committee model implemented in at least 75% of all wards | New Ward Committee model implemented in at least 90% of all wards | Number of Wards in municipalities implementing the new Ward Committee Model | Municipalities to indicate resources |
|  |  |  | Strengthening ward committees in rural and traditional areas and communities | COGTA DTA to facilitate the active participation of traditional leadership structures in ward committees to deepen democracy | Develop a plan to facilitate the active participation of traditional leadership structures in ward committees | Implement the plan to facilitate the active participation of traditional leadership structures in ward committees in 30% of all traditional community areas | Implement the plan to facilitate the active participation of traditional leadership structures in ward committees in 75% of all traditional community areas | Implement the plan to facilitate the active participation of traditional leadership structures in ward committees in at least 90% of all traditional community areas | Number of traditional leadership structures participating in ward committees | COGTA: Resources available |

| OUTPUTS AND OUTPUT DEFINITIONS | NATIONAL DELIVERABLES | PROVINCIAL BASELINE | PROVINCIAL ACTIVITIES | ACTIONS: COGTA & Partners | Provincial Target 2010/11 | Proposed Target 2011/12 (subject to budget approval) | Proposed Target 2012/13 (subject to budget approval) | Proposed Target 2013/14 (subject to budget approval) | INDICATOR | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT 6: Administrative and Financial capability | Strengthened anti-corruption capacities of municipalities | AG audit outcome 2008/09 | Ensure greater transparency, fight corruption and promote good financial management in Local Government | COGTA, OTP and PT Support the review of anti-corruption legislation as it relates to Local Government | Anti-Corruption legislation reviewed by 31 March 2011 | Anti-corruption policy legislation strengthened (inclusive of SCM regulatory environment) and progressively implemented in all municipalities | Quality assurance programme developed for oversight of implementation of anti-corruption legislation and policy | Monitoring of implementation of anti-corruption legislation and policy in municipalities | Anti-corruption legislation reviewed by target date Annual reports of the implementation and compliance with the anti-corruption local government legislation | DCoG: resources available allocated |
|  |  |  |  | COGTA, OTP, PT Anti-Corruption strategies and programmes developed and implemented in provincial depts. and municipalities | COGTA AND OTP and municipalities review anti-corruption strategies and plans | Implementation of revised anti-corruption strategies and plans | Implementation of revised anti-corruption strategies and plans | provincial depts. and all municipalities have anti-corruption strategies/fraud prevention plans | Number of anti-corruption strategies in place within municipalities and provincial depts. | Provincial depts. Municipalities to indicate resources |
|  |  |  |  | Municipalities: Municipal Public Accounts Committees established | All municipalities develop plans to establish Municipal Public Accounts Committees by December 2010 | 50% of municipalities establish Municipal Public Accounts Committees | 80% of municipalities establish Municipal Public Accounts Committees | 100% of municipalities establish Municipal Public Accounts Committees | Number of MPAC’s established by target date. | Municipalities to indicate resources |
| OUTPUT 6: (CONT) | Municipalities with unqualified audits increased from 53% to 100% | Audit outcomes: (2008/9) Disclaimers: 5 Qualified: 6 Unqualified: (with other matters): 9 Audit outcomes: (2008/9) Disclaimers: 5 Qualified: 6 Unqualified: (with other matters): 9 | Ensure greater transparency, fight corruption and promote good financial management in Local Government Ensure greater transparency, fight corruption and promote good financial management in Local Government | Professional Associations (IMFO, SAICA etc) Support municipalities to obtain clean audits | Enter into partnership agreements with COGTA and PT or municipalities to support Operation Clean Audit 2014 Sign MoU with UJ and Turfloop | Implement partnership agreements to support Operation Clean Audit 2014 | Implement partnership agreements to support Operation Clean Audit 2014 | Implement partnership agreements to support Operation Clean Audit 2014 | Number of partnership agreements entered into Number of municipalities supported | Professional bodies to indicate resources |
|  | Municipalities with unqualified audits increased from 53% to 100% (cont) |  |  | COGTA with Prov Treasury Support Support municipalities to obtain clean audits by target date | Support 21 municipalities to obtain clean audits | Support 75% municipalities to obtain clean audits | Support 90% municipalities to obtain clean audits | Support 100% of municipalities to obtain clean audits | Number of municipalities supported to obtain clean audits by target date | COGTA: Resources available Prov Treasury to indicate |
|  |  |  |  | Municipalities: Improve financial management and reduce qualified, disclaimer and adverse audit opinions | 60% of municipalities have clean audits | 75% of municipalities have clean audits | 90% of municipalities have clean audits | Municipalities with clean audits increased from 53% to 100% | Percentage municipalities with clean audits | Municipalities to indicate resources |
|  |  |  |  | Municipalities: Establish functional Audit Committee in municipalities | All municipalities adopt resolutions to establish functional Audit Committees by November 2010 | 75% of municipalities establish functional Audit Committees | 90% of municipalities establish functional Audit Committees | 100% of municipalities establish functional Audit Committees | % of municipalities with functional Audit Committees | Municipalities to indicate resources |
|  | Average monthly collection rate on billings to rises to 90% | The average payment rate is approx 64%. This % is however unconfirmed due to the inconsistencies of Municipalities to report in terms of Section 71 of the MFMA to National and Provincial Treasury. | Improve on the municipal billing system Collection rate of 90% | Municipalities: Develop and implement billing enhancement programmes Improve collection rates | Average monthly collection rate on billings to rise to 45% (75%) | Average monthly collection rate on billings to rise to 70% | Average monthly collection rate on billings to rise to 80% | Average monthly collection rate on billings to rise to 90% | Average monthly collection rate on billings | Municipalities to indicate resources |
|  |  |  |  | COGTA & Provincial Treasury: Support municipalities to improve collection rates | Support programmes to achieve the target of an average monthly collection rate on billings to rise to 50% | Support programmes to achieve the target of an average monthly collection rate on billings to rise to 70% | Support programmes to achieve the target of an average monthly collection rate on billings to rise to 80% | Support programmes to achieve the target of an average monthly collection rate on billings to rise to 90% | Number of municipalities supported to improve collection rates | COGTA: Resources available Prov Treasury to indicate |
| OUTPUT 6: (CONT) | The % of municipalities with debtors more than 50% of own revenue to be reduced from 14% to 12% | PT to provide | Improve revenue management in municipalities Reduce outstanding debt by 85% | Municipalities: Reduce outstanding debtors | % of municipalities with debtors more than 50% of own revenue to be reduced from 24% to 20% | % of municipalities with debtors more than 50% of own revenue to be reduced from 20% to 16% | % of municipalities with debtors more than 50% of own revenue to be reduced from 16% to 14% | % of municipalities with debtors more than 50% of own revenue to be reduced from 14% to 12% | % of municipalities with debtors of more than 50% of own revenue | Municipalities to indicate resources |
|  |  |  |  | COGTA & Provincial Treasury: Support municipalities to reduce outstanding debtors | Develop a support programme to support municipalities to reduce outstanding debtors in line with national targets | Implement the programme to support municipalities to reduce outstanding debtors in line with national targets | Implement the programme to support municipalities to reduce outstanding debtors in line with national targets | Implement the programme to support municipalities to reduce outstanding debtors in line with national targets | % of municipalities with debtors of more than 50% of own revenue | COGTA: Resources available Prov Treasury to indicate |
|  | The % of municipalities that are overspending on OPEX to improve from 5% to 4%. | PT to provide | Improve cash flow management in municipalities | Municipalities Improve cash flow management | % of municipalities that are overspending on OPEX to improve from 8% to 7%. | % of municipalities that are overspending on OPEX to improve from 7% to 6%. | % of municipalities that are overspending on OPEX to improve from 6% to 5%. | % of municipalities that are overspending on OPEX to improve from 5% to 4%. | % of municipalities that are overspending on OPEX | Municipalities to indicate resources |
|  |  |  |  | COGTA & Provincial Treasury: Support municipalities to improve cash flow management | Develop a support programme to support municipalities to improve cash flow management in line with national targets | Implement the programme to support municipalities to improve cash flow management in line with national targets | Implement the programme to support municipalities to improve cash flow management in line with national targets | Implement the programme to support municipalities to improve cash flow management in line with national targets | Number of municipalities supported to meet cash flow management targets | COGTA: Resources available Prov Treasury to indicate |
|  | The % of municipalities under spending on CAPEX to be reduced from 69% to 30% | 63% | Improve expenditure on the Capital Budget | Municipalities: Improve expenditure on the capital budget | % of municipalities under spending on CAPEX to be reduced to 70% | % of municipalities under spending on CAPEX to be reduced from 55% to 47% | % of municipalities under spending on CAPEX to be reduced from 47% to 39% | % of municipalities under spending on CAPEX to be reduced from 69% to 30% | % of municipalities under spending on CAPEX | Municipalities to indicate resources |
| OUTPUT 6: (CONT) | The % of municipalities under spending on CAPEX to be reduced from 69% to 30% (cont) | 63% | Improve expenditure on the Capital Budget (cont) | COGTA & Provincial Treasury: Support municipalities to improve expenditure on the capital budget | Develop a support programme to support municipalities to improve expenditure on the capital budget in line with national targets | Implement the programme to support municipalities to improve expenditure on the capital budget in line with national targets | Implement the programme to support municipalities to improve expenditure on the capital budget in line with national targets | Implement the programme to support municipalities to improve expenditure on the capital budget in line with national targets | Number of municipalities supported to meet national targets | COGTA: Resources available Prov Treasury to indicate |
|  | The % of municipalities spending less than 5% of OPEX on repairs and maintenance to be reduced from 58% to 45%. | PT to provide | Improve expenditure on repairs and maintenance | Municipalities: Improve expenditure on repairs and maintenance | % of municipalities spending less than 5% of OPEX on repairs and maintenance to be reduced from 92% to 85%. | % of municipalities spending less than 5% of OPEX on repairs and maintenance to be reduced from 85% to 70%. | % of municipalities spending less than 5% of OPEX on repairs and maintenance to be reduced from 70% to 58%. | % of municipalities spending less than 5% of OPEX on repairs and maintenance to be reduced from 58% to 45%. | % OPEX of spent on maintenance and repairs | Municipalities to indicate resources |
|  |  |  |  | COGTA & Provincial Treasury: Support municipalities to Improve expenditure on repairs and maintenance | Develop a support programme to support municipalities to improve expenditure on repairs and maintenance in line with national targets | Implement the programme to support municipalities to improve expenditure on repairs and maintenance in line with national targets | Implement the programme to support municipalities to improve expenditure on repairs and maintenance in line with national targets | Implement the programme to support municipalities to improve expenditure on repairs and maintenance in line with national targets | Number of municipalities supported to meet national targets | COGTA: Resources available Prov Treasury to indicate |

| OUTPUTS AND OUTPUT DEFINITIONS | NATIONAL DELIVERABLES | PROVINCIAL BASELINE | PROVINCIAL ACTIVITIES | ACTIONS: COGTA & Partners | Provincial Target 2010/11 | Proposed Target 2011/12 (subject to budget approval) | Proposed Target 2012/13 (subject to budget approval) | Proposed Target 2013/14 (subject to budget approval) | INDICATOR | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTPUT 7 Single window of Coordination established for review of policy and legislation, revision of planning, improved intervention and support mechanisms and alignment of capacity building programmes within government | A revised and comprehensive National Capacity Building Framework (NCBF) for local government | None | Roll-out of rapid response as part of provincial support | DCoG Review all capacity building and training initiatives aimed at local government Coordination of all capacity supporting initiatives and resources e.g. Siyenza Manje Programme Donor supported programmes DCoG programs | Audit of all capacity interventions finalised and coordination programme implemented Undertake review of LOGOLA, LGSETA, PALAMA, SALGA capacity building programmes, Siyenza Manje and other initiatives directed at municipalities by March 2011 | Develop and implement a revised and comprehensive National Capacity Building Framework (NCBF) for local government Rapid Response rolled out | Implement a revised and comprehensive National Capacity Building Framework (NCBF) for local government | Monitoring of Implementation of revised programme | Capacity Building Implementation Framework aligned to the NCBF and LGTAS by target date Training and and capacity building programmes of key partners aligned to the LGTAS and the revised NCBF | DCoG All relevant National Departments All relevant Provincial Departments SALGA PALAMA LGSETA DBSA Professional Bodies (ILGM, IMFO etc) Donors (EU, GTZ etc) |
|  |  |  |  |  | Implementation protocols signed with departments |  |  |  |  |  |